**Mission Possible Health - Monitoring of the project:**

**Responsible teacher: Zacharias Koutoulakis**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Month | Activity | Teacher | Time | Participants  | Documentation |
| September2017Preparatory activities | 1) The Directorate of Secondary Education of Chania and the director with the teachers from the school will be informed about receiving financing  | Zacharias Koutoulakis, Maria Papadaki | 11-9-2017 | Students at school, parents, teachers, people who are interested in our school and our project. | Emails |
| 2) Contacts will be established with the supporting institutions | Zacharias Koutoulakis, Maria Papadaki | 12-30 September 2017 | Orthodox Academy of Crete, Professional School of Education, Municipality of Platanias, Technical University of Crete, students at school, parents. | E-mails and phone calls |
| 3) In the curriculum of general education they will take into account the contents resulting from the ongoing project | Zacharias Koutoulakis, Maria Papadaki | 12-30 September2017 | Students at school, parents, teachers | Written Reports |
| 4) To establish the project teams (Agreement on the method and the frequency of communication) | Zacharias Koutoulakis, Maria Papadaki, Maria Manousaki, Elpiniki Michaloudi, Stylianos Papadakis | 12-30 September2017 | Project team and other students, teachers and parents | Written Reports |
| 5) Is confirmed allocation of tasks in project management at the level of schools | Zacharias Koutoulakis, Maria Papadaki, Maria Manousaki, Elpiniki Michaloudi, Stylianos Papadakis | 12-30 September2017 | Project team and other students, teachers and parents | Written Reports |
| 6)Prepatory regulations of recruitment and participation in the project | Zacharias Koutoulakis, Maria Papadaki, Maria Manousaki, Elpiniki Michaloudi, Stylianos Papadakis | 12-30 September2017 | 2nd and 3rd Grade students, Project team and other students and teachers | Written Reports |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Month | Activity | Teachers | Time | Participants  | Documentation |
| October | 1) schools conduct the recruitment of participants (the list of primary and reserve list) 2) making the information on the board of Erasmus+ and the school website3) prepare a presentation about the school, city, 4) TPM at Ordizia | Zacharias Koutoulakis, Maria Papadaki, Maria Manousaki, Elpiniki Michaloudi, Stylianos Papadakis | 1-31 October2017 | Project team and other students, teachers and parents, teachers of project partner schools. | School website, project website,photos, pictures, reports |
| November | 1) Gathering materials for presentations2) Meeting of the students for the project3) Evaluation questionaire (1st time) | Zacharias Koutoulakis, Maria Papadaki, Maria Manousaki, Elpiniki Michaloudi, Stylianos Papadakis | 1-30 November2017 | Project team and other students, school teachers, teachers of project partner schools. | Photos, Videos, Presentations |
| December | 1) Working on the presentations2) Preparing video for the Erasmus+ Project  | Zacharias Koutoulakis, Maria Papadaki, Maria Manousaki, Elpiniki Michaloudi, Stylianos Papadakis | 1-22 December2017 | Project team and other students, school teachers, teachers of project partner schools. | Written Reports, Video records, Presentations |
| January | 1) Visit to the museum of Cretan Herbs2) Evaluation questionnaire (2nd time)3) Preparing articles for the webpage and the  local press.4) Preparing materials for the project5) Submission of materials to the project site | Zacharias Koutoulakis, Maria Papadaki, Maria Manousaki, Elpiniki Michaloudi, Stylianos Papadakis | 8-31 January2018 | Project team and other students, school teachers, teachers of project partner schools, parents. | Photos, Video, Written Reports, Presentations,Publication in the Local Press |
| February | 1. Visit to Old Market of Chania
2. Interview with Botanist
3. Drawing local (Cretan) herbs
4. Visit to a Cooking Course - Professional School of Education of Chania
5. Dancing local (Cretan) dances
6. Singing Greek songs
7. Making Kahoot Quiz
 | Zacharias Koutoulakis, Maria Papadaki, Maria Manousaki, Elpiniki Michaloudi, Stylianos Papadakis | 1-28 February 2018 | Project team and other students, school teachers, teachers of project partner schools, parents. | Photos, Video, Written Reports, Presentations, Publication in the Local Press |