**Mission Possible Health – Monitoring of the project:**

**Responsible teacher: Monika Wysoczańska**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Month** | **Activity** | **Teacher** | **Time** | **Participantsor recipient** | **Documentation** |
| September2017preparatory activities | 1. Directorates and the authorities from the schools will be informed about receiving financing.
 | Agnieszka Oleszczuk, Agnieszka Pryboda |  04.09.2017 | Students at school, parents, teachers, people who are interested in our school and our project. | E-mails |
| 1. Contacts will be established with the supporting institutions.
 | Agnieszka Oleszczuk, Agnieszka Pryboda | 04-15 September 2017 | CWM in Grodno, Educational Centre of Ecology in Szczecinek,, Ostrowice commune, newspaper, a local expert in Herbs, students at school, parents. | E-mails, phone calls  |
| 1. In the curriculum of general education they will take into account the contents resulting from the ongoing project.
 | Agnieszka Oleszczuk, Agnieszka Pryboda, Monika Wysoczańska, Małgorzata Nowak, Łukasz Grochowski | 04-15 September2017 | Students at school, parents, teachers. | Written Reports |
| 1. To establish the project teams (Agree on the method and frequency of communication).
 | Agnieszka Oleszczuk, Agnieszka Pryboda, Monika Wysoczańska, Małgorzata Nowak, Łukasz Grochowski | 15-30 September2017 | Project team and other students, teachers and parents. | Written Reports |
| 1. Is confirmed allocation of tasks in project management at the level of schools.
 | Agnieszka Oleszczuk, Agnieszka Pryboda, Monika Wysoczańska, Małgorzata Nowak, Łukasz Grochowski | 15-30 September2017 | Project team and other students, teachers and parents. | Written Reports |
| 1. Preparatory regulations of recruitment and participation in the project.
 | Agnieszka Oleszczuk, Agnieszka Pryboda, Monika Wysoczańska, Małgorzata Nowak, Łukasz Grochowski | 15-30 September2017 | Students at school, project team and other students and teachers  | Written Reports  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Month** | **Activity** | **Teacher** | **Time** | **Participantsorrecipient** | **Documentation** |
| October 2017 | 1. Schools conduct the recruitment of participants.
2. Making the information on the board Erasmus+ and the school website.
3. Prepare a presentation about the school.
4. TPM w Ordizia in Spain.
5. Trip to the Wolinski National Park.
6. We make vegetable and fruit juices.
7. Creating a project website.
 | Agnieszka Oleszczuk, Agnieszka Pryboda, Monika Wysoczańska, Małgorzata Nowak, Łukasz Grochowski | 01-31 October2017 | Project team and other students, teachers and parents, teachers of project partner schools. | School website, project website, photos, pictures, reports |
| November 2017 | 1. Survey ex-ante topic 1 Herbs and spaces.
2. Gathering materials for presentation.
3. Meeting of the students for the project.
4. Trip to the Wolinski National Park.
5. Presentation of the Erasmus + Mission Possible Health project idea to other students.
6. We prepare healthy, full of herbs and spices, sandwich pastes.
 | Agnieszka Oleszczuk, Agnieszka Pryboda, Monika Wysoczańska, Małgorzata Nowak, Łukasz Grochowski | 01-30 November2017 | Project team and other students, school teachers, teachers of project partner schools. | Photos and Video records |
| December 2017 | 1. Work on the presentation.
2. Selecting the best Erasmus + Mission Possible Health logo.
3. A visit to the Center of Ecological Education in Szczecin.
4. We bake cookies with spices.
 | Agnieszka Oleszczuk, Agnieszka Pryboda, Monika Wysoczańska, Małgorzata Nowak, Łukasz Grochowski | 01-31 December2017 | Project team and other students, school teachers, teachers of project partner schools. | Written Reports, photos |
| January2018 | 1. Evaluation questionnaire (2nd time).
2. Preparing materials for the project.
 | Agnieszka Pryboda, Monika Wysoczańska | 01-12 January2018 | Project team and other students, school teachers, teachers of project partner schools. | Written Reports, photos |
| February 2018 | 1. We make soaps and creams.
2. Visit to the E(x)plory Science Festival in Szczecin.
3. Interview with a herbalist.
4. Performing a multimedia presentation about herbs and spices.
5. We prepare national dances.
6. We are preparing to go to Turkey
7. Presentation of results for the school community.
8. Preparing a photo exhibition.
9. Preparing articles about the design work for the press.
10. Prepare work cards for herbal and spice activities.
11. Preparing materials for the newsletter.
12. Submission of materials to the project site.
 | Agnieszka Oleszczuk, Agnieszka Pryboda, Monika Wysoczańska, Małgorzata Nowak, Łukasz Grochowski | 1-28 February2018 | Project team and other students, school teachers, teachers of project partner schools, parents and school visitors. | Photos, Video,Written Reports, presentation, publication in the Local Press |