Mission Possible Health - Monitoring of the project:
Responsible teacher: Ion Unanue
Month	Activity	Teacher	Time	Participants or recipient	Documentation
September / 2017 / preparatory activities	1) Directorates and the authorities from the schools will be informed about receiving financing	Ion Unanue / Larraitz Garmendia	01-15 September	Teachers, people who are interested in our school and our project.	Oral meetings, school website
	2) contacts will be established with the supporting institutions	Emin KUTLU / Akın ACAR	01-15 September	D’elikatuz center, Goierriko hitza newspaper, a local expert in Herbs, Students at school, parents.	E-mails, phone calls and meetings
	3) in the curriculum of general education they will take into account the contents resulting from the ongoing project	Gorka Sarasola / Ione Murumendiaraz / Koro Irastorza / Josune Sarasola	01-15 September	Students at school, teachers	Written Reports, E-mails
	4) to establish the project teams (Agree on the method and frequency of communication)	Gorka Sarasola / Ione Murumendiaraz / Koro Irastorza / Josune Sarasola / Amaia Anabitarte	15-30 September	Project team and other students, teachers and parents	Written Reports
	5) is confirmed allocation of tasks in project management at the level of schools	Ion Unanue / Larraitz Garmendia, / Nerea Azurmendi	15-30 September	Project team and other students, teachers and parents	Written Reports
	6) preparatory regulations of recruitment and participation in the project	Ion Unanue, Larraitz Garmendia	15-30 September	1st baccalaureate grade students, Project team and other students and teachers	Written Reports and power point presentations

Month	Activity	Teacher	Time	Participants or recipient	Documentation
October	1) schools conduct the recruitment of participants / 2) making the information on the board Erasmus+ and the school website / 3) prepare a presentation about the school / 4) 1st transnational meeting in Jakintza ikastola	Gorka Sarasola, / Koro Irastorza, / Josune Sarasola, / Nerea Azurmendi, / Mikel Etxarri, / Ion Unanue, / Larraitz Garmendia	1-31 October / 2018	Project team and other students, teachers and parents, teachers of project partner schools.	School website, project website, photos, pictures, reports, newspaper
November	1) Survey ex-ante topic 1 Herbst and spaces / 3) Gathering materials for presentation	Ione Muruamendiaraz, / Ion Unanue, Larraitz Garmendia	1-30 November / 2018	Project team and other students, school teachers, teachers of project partner schools.	Photos and Video records
December	1) Work on the presentation / 2) Football championship to measure physical activity / 3) School and town presentation video	Angel Cuerdo, / Gorka Sarasola / Ione Murumendiaraz, / Ion Unanue, / Larraitz Garmendia	1-31 December / 2018	Project team and other students, school teachers.	PPT presentation, photos
January	1) Presentation of results for the school community / 2) preparing a photo exhibition / 3) evaluation questionnaire / 4) preparing articles about the design work for the press. / 5) Prepare work cards for herbal and spice activities / 6) preparing materials for the newsletter / 7) submission of materials to the project site	Ione Murumendiaraz, / Ion Unanue, / Larraitz Garmendia	1-15 January / 2018	Project team and other students, school teachers	Photos, Video, Written Reports, PPT presentation, exhibition posters